## Sheet1
GENERAL | OVERVIEW | DETAILS/NOTES
Name of Event
Strategic Goal
Primary Committee
Secondary Committee
Date
Start Time
End Time
Location
Number of Attendees (min)
Number of Attendees (max)
Speaker(s)
Speaker Accommodations
Speaker Travel
Speaker Requests
Topics
Special Permit(s)
Special Insurance
VENUE
Request for Proposal(s) | Staff
Review contract vs. budget | Staff
Venue layout(s) | Staff
Parking/Access | Staff
Valet Vendor | Staff
Tables/Table cloths, cups, utensils | Staff
Food and Beverage | Staff/Committee
Linens and other services | Staff/Committee
EQUIPMENT/SERVICES
Podium(s)
PA (Audio) system
Video Projector(s)
Projection Screen(s)
Computer/laptops
Internet/WIFI
Gobo Requirements
SERVICES/TALENT
Photographer(s)
Videographer(s)
MARKETING
Upload event on website | Staff
E Charrette | Staff
Email Blast(s) | Staff
Direct Mail (USPS) | N/A
Sponsorship Promotion | Staff and Volunteers
Attendance Promotion | Staff and Volunteers
SPONSORSHIP
Sponsorship Goal | Staff/Committee
Sponsorship benefits fulfillment | Staff/Committee
Sponsors sales | Staff/Committee
Email promotions | Staff
ATTENDANCE STATUS
Ticket sales status | Staff
Count to venue/order food/dietary needs | Staff
PART I
PART II
FINALIZE EVENT AGENDA
Check-in/Registration | Staff/Committee
Opening | Staff
Food Service | Staff
Presentation(s) | Committee
Closing | Staff
TWO WEEKS BEFORE EVENT
Final Printing Orders:
Admission Tickets | N/A
Drink Tickets | Staff
Dessert Inserts | Staff
Wine Tags | Staff
Programs/Handouts | Staff
Signage | Staff
Script/ Agenda | Staff
Step & Repeat Backdrop | N/A
ONE WEEK BEFORE EVENT
Communicate Parking Details | Staff
Rehearsal | Staff/Committee
Review/Finalize script | Staff/Committee
Prepare Final Count for Venue | Staff
BRING TO EVENT
Registration/Check-in List(s) | Staff
Computer/Laptop | Staff
Powerpoint/Video | Staff
Display Board(s) | Staff
Sign(s) | Staff
Big Checks | Staff
Table Signs | Staff
Payment Check(s) | Staff
Credit Card/Blank Checks | Staff
Parking passes | Staff
Square/Card Reader | Staff
DAY OF EVENT
Send final event reminder/special instructions | Staff
Meet with Venue staff | Staff
Meet with Committee/Volunteers | Staff
Place signage | Staff
Verify Venue has met specs | Staff
Test AV/Lighting Equip | Staff
Verify Final Deliveries | Staff
Verify Service/Talent Schedules | Staff
Verify Parking/attendants/valet/passes | Staff/committee/volunteers/talent
Final walk-through/rehearsal | Staff/committee/volunteers/talent
DURING EVENT
Check in Guests | Committee
Issue Name Badges/ID | Staff
Monitor Traffic Flow | Staff
Monitor Guest satisfaction | Staff
Take Photos | Photographer(s)
EVENT CONCLUSION
Collect/Remove Chapter Items | Staff
Settle Account with Venue | Staff
Settle with Service/Talent | Staff
POST EVENT
Document Comments & Criticism | Staff/Committee
Ideas & Data | Staff/Committee
Send survey out to attendees | Staff
Deposit any cash received | Staff
Report mileage and times | Staff
Process final payments | Staff
Schedule post event analysis with committee | Staff/Committee